# Go-live plan — from today (2026-07-16) to production

This is the execution plan for getting Storefront live, fully off Replit, with real auth and real data — and for wiring in the rest of Headout's tool/skill landscape. It's written against the actual current state of this repo, not the aspirational one, so every step below is grounded in a specific file, env var, or commit already sitting in the working tree.

Scope: ship the existing Vite + Express prototype, fully decoupled from Replit, live on Railway with real Guardian auth and a real Postgres.

## 0. Ground truth — what's actually true right now

Verified directly against the working tree, not memory:

| Component | Current reality | Target | Status |
| --- | --- | --- | --- |
| Anthropic client | lib/integrations-anthropic-ai/src/client.ts and artifacts/api-server/src/lib/anthropicClient.ts have already been edited (uncommitted) to fall back from the Replit AI_INTEGRATIONS_ANTHROPIC_* vars to standard ANTHROPIC_API_KEY/ANTHROPIC_BASE_URL/CLAUDE_MODEL. | Standard Anthropic env vars only, no Replit dependency. | ~90% done, uncommitted. Needs a real key + one eval-harness fix (see 2.2). |
| Auth | artifacts/api-server/src/lib/auth.ts:8 hardcodes ISSUER_URL = "https://replit.com/oidc" and getOidcConfig() calls client.discovery(new URL(ISSUER_URL), process.env.REPL_ID!) — `REPL_ID` is a Replit-runtime-only variable. This is Repl Auth, not swappable by env var; it categorically cannot issue a working login flow off Replit. | Guardian (Ory-backed) SSO — Headout's actual SSO standard, not raw OAuth. | Not started; hard blocker. Reference implementation already pulled into .guardian-kit-tmp / .headauth-tmp (see 0.1). This is the one piece of "auth is Replit" that's a real rewrite, not a config change. |
| Database | Drizzle + pgvector, schema in lib/db. lib/db/scripts/ensure-extension.mjs (new, uncommitted) creates the vector extension before push; lib/db/package.json has a new migrate script wired into railway.json's preDeployCommand. | Railway Postgres with pgvector, migrated + seeded on deploy. | Scaffolded, uncommitted, unverified against a real Railway Postgres instance. |
| Catalogue seed data | artifacts/api-server/src/lib/realSeedData.ts (1509 lines, committed in b5d28b9) already has 89 real Headout tools: Delphi, Argus (+ Argus MCP), Guardian, Product OS, Zenith, Medusa, plus 37 real Claude Code skills pulled from HeadoutAgentsConfig's bundles.json. artifacts/api-server/src/scripts/seedRealTools.ts (pnpm run seed:real) wipes and reseeds the tools table with it. | Same data, actually run against the production DB. | The content work is basically done. What's missing is running it against a real deployed DB — see 2.1. lib/seedData.ts (fictional) stays untouched on purpose — it's the eval harness's regression fixture set. |
| Deploy | Dockerfile (new, uncommitted) builds one Debian-based image: pnpm --filter storefront build (Vite → static) + pnpm --filter api-server build (esbuild bundle), Express serves both the API and the static SPA from one origin. railway.json (new, uncommitted) points at it, with a healthcheckPath: /api/healthz and a preDeployCommand that runs the DB migration. | Same — single service, no CORS/proxy config to maintain. | Drafted, uncommitted, never deployed. |
| Embeddings | Local ONNX model (onnxruntime-node), no external dependency. Dockerfile already installs libgomp1 for it. | Unchanged. | Fine as-is. |
| Scratch reference clones | .guardian-kit-tmp (partial/sparse clone of github/headout/Guardian-App-Starter-Kit, widened during this session to artifacts/api-server + .agents) and .headauth-tmp (full clone of github/headout/headauth, the actual @headout/headauth npm package) are sitting in the working tree, untracked. .codex/ is an unrelated Codex CLI config dir. | Extract what's needed (below), then delete all three — they should never be committed. | Reference material only — not part of the app. |

### 0.1 What the Guardian/Ory auth model actually looks like (from the starter kit)

This is materially different from the current Replit OIDC flow, so the "swap" is a rewrite, not a config change:

- No login form, no `/login`/`/callback` routes, no server-side OIDC dance. The frontend redirects straight to Ory's hosted login (${VITE_ORY_SDK_URL}/ui/login?return_to=...). Ory owns the entire login UI.

- No server-side session store. The Ory session is a cookie the browser already has after login. The backend's only job is to forward that cookie to Guardian (https://guardian.headout.com) via POST /auth/whoami, which returns the user's identity. There is no token refresh logic, no sessionsTable needed for this.

- The application must be registered with Guardian as an `OryApplication` enum value (existing values: ARIES, SUPPLIERS, RECON, BMS, ... — STOREFRONT is not in the list yet). This is a platform-team ask, not something we can self-serve.

- The Ory session cookie is domain-scoped (almost certainly to .headout.com or auth.headout.com's cookie domain policy). If Storefront is served from a bare Railway domain (*.up.railway.app), the browser will not send that cookie to it. A `storefront.headout.com` custom domain is a hard prerequisite for auth to work at all — this elevates the "subdomain provisioning" ask in PLATFORM-TEAM-REQUIREMENTS.md §11 from P1/P2 to a Phase-1 blocker.

- Dev-mode bypass exists (ORY_SESSION_TOKEN, a real cookie value copied out of a logged-in browser session, injected via a Vite dev-only endpoint) — needed so local dev doesn't require going through Ory's hosted domain.

- The one genuinely good piece of news: the current frontend already isolates auth behind a single context (artifacts/storefront/src/lib/auth-context.tsx wraps one hook in AuthProvider/useAuthContext). Every consumer (App.tsx, Sidebar.tsx, HomeChat.tsx, conversations-context.tsx, landing.tsx) only calls useAuthContext(). The blast radius of the auth rewrite is one context file + the server routes/middleware — not every component.

## 2. Phase 1 — Ship the current prototype, fully off Replit, live on Railway

Goal: the existing Vite+Express app, running on Railway, at storefront.headout.com, with real Guardian auth, a real seeded Postgres, and a real Anthropic key. This is the whole build — no Next.js rewrite.

### 2.1 Database — provision, migrate, seed

1.  Provision a Railway Postgres instance (or attach an existing pgvector-capable one). Verify pgvector is actually allowed — some managed Postgres offerings block arbitrary CREATE EXTENSION; Railway's own Postgres template does support it, but confirm before relying on ensure-extension.mjs.

2.  Set DATABASE_URL in the Railway service's environment.

3.  Commit the already-drafted lib/db/scripts/ensure-extension.mjs and the migrate/ensure-extension scripts in lib/db/package.json (currently uncommitted diffs).

4.  Confirm railway.json's preDeployCommand: "pnpm --filter @workspace/db run migrate" runs ensure-extension then drizzle-kit push --force — this is already wired, just needs a live DB to run against.

5.  Run `pnpm run seed:real` (in artifacts/api-server/package.json) against the provisioned DB. This is the "add skills from across Headout" step — the content (89 tools incl. Delphi, Argus, Guardian, Product OS, Medusa, Zenith, 37 HeadoutAgentsConfig skills) is already written; it just has never been executed against a real deployed database. Do this once, then decide a refresh cadence (monthly? on every HeadoutAgentsConfig bundle change?) — not decided yet, flag as an open question in §5.

6.  Leave lib/seedData.ts / the fictional seed alone — it's catalogueQuality.test.ts's regression fixture, not production content.

### 2.2 Anthropic / Claude — finish and verify

1.  Commit the already-made changes to lib/integrations-anthropic-ai/src/client.ts and artifacts/api-server/src/lib/anthropicClient.ts.

2.  Set ANTHROPIC_API_KEY (real key, ask #4 above) in Railway. Leave ANTHROPIC_BASE_URL unset unless routing through a gateway (per PLATFORM-TEAM-REQUIREMENTS.md §6, OpenRouter/internal gateway status is still unconfirmed — config swap, not a rewrite, when it lands).

3.  Fix a real gap found in this audit: artifacts/api-server/src/eval/gate3Routing.test.ts, buildHandoff.test.ts, and gate3Latency.test.ts all gate their AI_READY check on process.env.AI_INTEGRATIONS_ANTHROPIC_BASE_URL specifically — the *legacy Replit var name*. Once Railway only sets ANTHROPIC_API_KEY (no base URL), these three eval suites will silently report AI_READY = false and skip themselves, instead of failing loudly. Update all three to check for ANTHROPIC_API_KEY (or equivalent), not the Replit-specific var name. This matters because the eval harness is explicitly "the regression net" per this repo's working agreements — a silently-skipped gate is worse than a failing one.

### 2.3 Auth — replace Repl Auth with Guardian (the real rewrite)

This is the biggest, riskiest piece of work in Phase 1. Concrete file plan, backend first:

Delete/replace:

- artifacts/api-server/src/lib/auth.ts — the whole OIDC-discovery + custom sessionsTable model goes away. No token refresh, no REPL_ID, no ISSUER_URL.

- artifacts/api-server/src/routes/auth.ts — /login and /callback are gone entirely (Ory's hosted UI owns login; the frontend redirects directly, no server round-trip). /mobile-auth/* is dropped unless ask #5 comes back "yes we need mobile."

- artifacts/api-server/src/middlewares/authMiddleware.ts — replaced by a requireAuth-style middleware that reads the Ory session cookie off the request and calls Guardian's /auth/whoami, populating req.auth = { user, rawCookie } (see the exact reference implementation pulled into .guardian-kit-tmp/artifacts/api-server/src/middlewares/require-auth.ts — copy the pattern, not the file verbatim, since this repo's route/response conventions differ slightly).

Add:

- artifacts/api-server/src/downstreams/guardian/client.ts + endpoints.ts — Guardian axios client + whoami/listUserResourcePermissions calls. Reference implementation: .guardian-kit-tmp/artifacts/api-server/src/downstreams/guardian/{client,endpoints}.ts.

- artifacts/api-server/src/lib/guardian-config.ts — env helpers for GUARDIAN_APPLICATION_NAME, ORY_SESSION_COOKIE_NAME.

- A GET /me-shaped route (can keep the existing /api/auth/user path to avoid touching the frontend's fetch URL — just change what it does internally: read the cookie, call Guardian, return the user).

- cookie-parser is already mounted (app.use(cookieParser()) is in app.ts today) — reusable as-is.

Frontend — small blast radius, thanks to the existing context wrapper:

- Rewrite artifacts/storefront/src/lib/auth-context.tsx to stop importing @workspace/replit-auth-web and instead: redirect to ${VITE_ORY_SDK_URL}/ui/login?return_to=... for login(), call Ory's logout flow for logout(), and call /api/auth/user for the current session (same shape as today — {user, isLoading, isAuthenticated, login, logout} — so App.tsx, Sidebar.tsx, HomeChat.tsx, conversations-context.tsx, landing.tsx need no changes).

- Delete lib/replit-auth-web once nothing imports it.

- Add @ory/client-fetch as a dependency (only if adopting @headout/headauth's AuthProvider/useAuth wholesale — otherwise a plain fetch-based rewrite of the existing hook is simpler and avoids pulling in Jotai, which this app doesn't currently use). Recommendation: don't adopt @headout/headauth's React layer (it assumes Jotai + a specific bootstrap-before-mount sequencing this app doesn't have); port the *pattern* (redirect-to-Ory, cookie-forwarding /me) into the existing auth-context.tsx shape instead. Flag if this turns out to be more work than expected once started.

Env vars to set in Railway (from ask #1): VITE_ORY_SDK_URL, ORY_SESSION_COOKIE_NAME, GUARDIAN_BASE_URL, GUARDIAN_APPLICATION_NAME=STOREFRONT.

Data model cleanup: once sessions are no longer stored server-side, sessionsTable in lib/db becomes dead — remove it in a follow-up pass once the new auth path is verified working (don't do this in the same PR as the swap; verify first).

### 2.4 Deploy — commit, connect, cut over

1.  Commit Dockerfile, railway.json, .dockerignore (currently untracked).

2.  Connect this GitHub repo to the Railway service for auto-deploy on push to main (confirm with platform team whether CI-triggered deploy or a gated deploy is their standard — PLATFORM-TEAM-REQUIREMENTS.md §2 P1).

3.  Point storefront.headout.com (ask #2) at the Railway service.

4.  Deploy. Verify /api/healthz (the configured healthcheck path) responds, then walk the three journeys by hand in the real deployed environment: discover → scope → modality routing; register-a-tool; browse.

5.  Verify login actually round-trips through Ory → Guardian → the app, in the real domain (this cannot be fully verified until the custom domain is live, per §0.1).

### 2.5 Clean up scratch state

- Delete .guardian-kit-tmp and .headauth-tmp once the patterns/code above have been extracted — they're reference clones, not app code, and shouldn't be committed.

- .codex/ is unrelated tooling config; leave it out of any commit (check .gitignore covers it, or remove it if it's just local scratch).

### 2.6 Phase 1 exit checklist

☐  All 5 currently-uncommitted diffs (app.ts, anthropicClient.ts, client.ts, pnpm-workspace.yaml, lib/db/package.json) committed

☐  Dockerfile, railway.json, .dockerignore, lib/db/scripts/ committed

☐  Real ANTHROPIC_API_KEY set in Railway; eval AI_READY gates fixed to not key off the Replit var name

☐  Railway Postgres provisioned, pgvector confirmed working, migrate + seed:real run successfully

☐  Guardian STOREFRONT application registered; storefront.headout.com live and pointed at Railway

☐  Full Guardian/Ory auth rewrite done and verified end-to-end on the real domain (not just locally)

☐  sessionsTable and lib/replit-auth-web removed once auth is verified stable

☐  .guardian-kit-tmp, .headauth-tmp deleted

☐  Eval harness (e2eConversations.ts) run against the live deploy and behaviorally matches the last known-good Replit run

## 3. Phase 2 — Wire the rest of the Headout tool/skill landscape

Most of the "seed the catalogue with Headout's tools" work is already done in code (§0, realSeedData.ts) — running seed:real in §2.1 covers content. What's left is *agent-side wiring*, not catalogue content:

1.  Give Storefront's own agents Delphi access. Per AGENT-TOOL-DEPENDENCIES.md, this means a PR to the HeadoutAgentsConfig repo adding Delphi to the relevant .mcp.json — not custom plumbing in this repo. This is the single highest-leverage upgrade to the critique/scope agent (Headout-grounded advice vs. generic PM advice).

2.  Confirm current Zeps connector/capability list before the scope agent keeps recommending Zeps for things it can't actually do yet (some connectors were still being wired per the hackathon writeup) — ask Rajasekhar or check via Delphi.

3.  Decide the Product OS boundary. Product OS already does PRD generation/ideation/validation — overlaps the critique/scope agent. Decide: hand off to it for deep PRD work, or stay deliberately lighter (quick scope → brief). Don't build a second Product OS by accident.

4.  Decide the scope agent's reuse of `feature-interview-ho`. Per the Delphi audit, feature-interview-ho (+ feature-interview-agent-ho) already does ~80% of structured requirements-gathering. Storefront's actual distinctive value is the *front* of the funnel (reuse-check → kill-or-reshape → modality choice) that hands off to feature-interview-ho for the spec, not a second implementation of the interview.

5.  Get the Guardian setup skill (guardian-auth, fully read out of .guardian-kit-tmp/.agents/skills/guardian-auth/SKILL.md during this audit) baked into the future scaffolding template — this is the actual skill referenced as "Rohan sharing" in CLAUDE.md; it's already in hand via the starter-kit clone, so this ask can be closed rather than chased.

6.  Seed refresh cadence decision (see open question in §5).

## 4. Phase 3 — Governance and hardening (post-launch, not blocking go-live)

Carried over from PLATFORM-TEAM-REQUIREMENTS.md §8 — explicitly not required for Phase 1 to ship, but needed before wider rollout:

- Resolve the three-gates design (publisher listing approval, ship-to-catalogue review, per-tool access approval) — currently an open design question, not just a platform ask.

- Get the org's security standards/checklist so template CI can enforce real rules (v1 substitute for Vulcan, which can't gate).

- Name the human reviewer(s) for Storefront-shipped tools.

- Approved third-party vendor + PII data-policy list, so the scope agent only ever recommends sanctioned vendors.

- Monitoring/alerting standard for deployed tools, so the Gateway's kill-switch/incident path has something real to hook into.

- Vulcan v2 (structured verdict, gate-capable) — roadmap item, revisit when it exists.

## 5. Open decisions that need a person, not more code

- Catalogue seed refresh cadence — one-time seed:real run, or scheduled resync against HeadoutAgentsConfig's bundles.json/GitHub org audit? Nothing currently automates this.

- Mobile auth (ask #5) — does Storefront need it? If not, drop the token-exchange routes instead of porting them to Guardian.

- Deploy gating — fully CI-auto-deploy on push to main, or a manual/gated promotion step? Affects how much of railway.json's deploy config is "real" vs. aspirational.

- `@headout/headauth` adoption — use the package wholesale (pulls in Jotai + its bootstrap-before-mount sequencing) vs. port just the pattern into the existing auth-context.tsx shape (recommended in §2.3, smaller diff, no new state-management dependency). Worth a quick decision before starting the auth rewrite, since it changes the shape of the PR.

## Docs this plan complements

- PLATFORM-TEAM-REQUIREMENTS.md/AGENT-TOOL-DEPENDENCIES.md — source material for §1 and §3, cross-referenced above with what's now resolved vs. still open.